## Feuil1
Action | WHAT | Who | Others | Priority
#1 | Write the minute of the meeting | Catherine | Hervé | H
#2 | Verify the grey list accommodate for BGC sensors | Thierry
#3 | Provide monthly snapshots for the metadata anomalies (Henry’s template) | Antoine
#4 | Produce Biogeochemical-Argo document (operational point of view, good practices) “BGC-Argo for dummies”. | Emmanuel | Antoine,Henry
#5 | Provide a documentation in FAQ that BGC-floats can surface at regular interval or specific time. | Henry
#6 | Write a cookbook for BGC trajectory Btraj | Catherine | Jean-Philippe |  | how: a document with a code flow chart
#7 | Provide sub-routines for calculation for variables and derived variables | Ken |  |  | how: a document with a code flow chart
#8 | Test netcdf4 format on merge file for the size | Thierry |  |  | how: a document with a code flow chart
#9 | Merge File (Bio and core profiles stored) write the documentation | Thierry
#10 | Interact with JCOMMOPS to improve the map representativeness. | Catherine | Henry, Mathieu, Anthonin |  | Table of parameter (B.King)
#11 | Develop a restricted user-list to share tools and codes | Catherine
#12 | investigate the development of Shared DM Tools | Catherine | Henry, Virginie |  | Table of parameter (B.King)
#13 | Investigate the quality of oxygen in the trajectory file to check whether we need to update the RT-QC test | all dm operators
#14 | Develop a QC test for hook O2 | Cathy | Virginie, Henry
#15 | Define an in air-based RT adjustment method for O2 | Henry | Ken, Seth |  | two products (B. king)
#16 | Update the Cookbook and the DOXY QC documents | Virginie
#17 | Finish the pressure dependence investigation of bromide absorption | Ken
#18 | Define an RT adjustment method for NO3 | Ken | Raphaelle, Catherine
#19 | Draft the QC documentation for NO3 | Ken | Catherine, Orens
#20 | Write the document processing pH at the DAC level | Ken | Catherine, Antoine
#21 | Define an RT adjustment method for pH | Ken | Raphaelle, Henry
#22 | Draft the QC documentation for pH | Ken | Catherine, Henry
#23 | Deep /dark fluorescence signal: develop an operational procedure (Xing et al., in press) for implementation in RT Update the documentation accordingly | Catherine | Emmanuel, Hervé
#24 | Deep /dark fluorescence signal: when CDOM data are available, implementation of a DM procedure | Xiao Gang | Herve
#25 | Finish the NPQ investigation | Emmanuel | Xiao gang, Hervé
#26 | Finish the investigation of the bias of factory calibration. Once published in peer-review literature, put the correction factor in the PREDEPLOYMENT_CALIB_XXX | Hervé | Emmanuel, Catherine
#27 | Test the feasibility of DM QC monitoring drift at depth (raw data) and OCR surface | Antoine | Emmanuel
#28 | Cross check of Chla and bbp for DM QC | Antoine | Emmanuel
#29 | DM: Cross checks Kd-derived Chla and Fchla for DM metrics | Antoine | Xiao gang, Emmanuel
#30 | Produce the documentation “processing CDOM at the DAC “level” (required for DM Chla) | Catherine | Emanuele
#31 | correct the khi , angle and sensor at the DAC level | Antoine | Uday, Ken, Rebecca
#32 | Update the processing “backscattering at the DAC level” document | Catherine | Emmanuel
#33 | Update Tables 25 and 27 with MCOMS and FLBB_2K | Catherine
#34 | Compare and investigate the reason for the values of bbp at depth derived by different DACS in similar region might differ | Antoine | Emmanuel
#35 | Test the feasibility of DM QC monitoring drift at depth (raw data) and OCR surface | Antoine | Emmanuel
#36 | Develop a RT procedure based on clear sky model for irradiance range | Antoine | Emanuele, Emmanuel
#37 | Draft the QC documentation for irradiance | Emmanuel | Emanuele, Catherine
#38 | DM: Take into consideration the temperature dependence of the sensor dark | Antoine | Nathan, Emanuele