## Feuil1
ADMT16 Action List Updated on the 21 Sep 2016 On 26 actions : 18 Done 3Partially 5 Not Done
| Action | Target Date | Responsibility | Priority | Status
1 | Revise the set of metrics proposed by Mathieu and Brian | AST17 | Brian, Sylvie, Mathieu, J Gilson, Katie Gowers, Pelle | R | A first version of the KPIs proposed by Mathieu has been implemented and will be discussed at AMTT17 no feedback on Brian metrics | p
2 | AIC to make the link with the Centers that are integrating and redistributing Argo data and be sure they use our adjusted data and use the flags and report to ADMT | ADMT17 | M Belbeoch | R |  | ?
Real Time Data Stream
3 | Centres with access to the GTS to compare files sent to files received at various nodes. Data is going missing and we don’t know where. Run comparison looking for all files sent in one or two days and DACs then need to provide list of what they sent onto the GTS in that time period. | AST17 | Anh with JMA, BOM,UK MET OFFICE, AOML, US-GODAE with all DACS | H | The test was done and a report was sent to the ADMT. Feedback will be provided at the meeting. There are still some issues with some DACs. From Coriolis: Once an hour, all new profile files are inserted in a BUFR message and sent on GTS. The BUFR encoder manages the primary profile of a cycle file. But it ignores the secondary profiles and the bio-profiles. Coriolis DAC is updating its version of BUFR encoder; the new version will manage primary, secondary and bio-profiles. | d
4 | Put the latest version of the BUFR encoders on the ADMT WWW pages All DACS to verify if they use the latest version of the Netcdf-BUFR converter | AST17 | Thierry/Kensaku Kobayashi/Anh All Dacs | H | Done: http://www.argodatamgt.org/Documentation/Tools Argo NetCDF converter to WMO-BUFR, developped by Japan Meteorological Agency (JMA) http://dx.doi.org/10.17882/45983 Argo NetCDF converter to WMO-BUFR, developped by the Department of Fisheries and Oceans Canada (DFO) http://dx.doi.org/10.17882/45985 | d
5 | Split the QC manuals in two : one for Core Argo managed by Thierry and Anny , one for Bio-Argo managed by Catherine and Virginie | AST17 | Annie and Catherine | R | done | d
6 | Change QC manual to only accept data with JULD >= 17167 and add range test to check that date is not later than NOW UTC. | AST17 | Annie and Catherine | R |  | ?
Reference Database
7 | Provide feedback on rejected CTDs back to CDHDO and NCEI | ADMT17 | Christine | R | Report sent on 2016/06/06 to CCHDO | d
8 | Screen Argo reference dataset contents to assess data or originator quality issues based on Christine's QC of the dataset. Exclude "bad" quality providers. | ADMT17 | Christine | R | a study has been made and will be presented at the meeting | d
9 | Label the source in the REF DB to facilitate to identification of high quality data. | ADMT17 | Christine | R | In the new version, new column qclevel in box files : COR for CORIOLIS, CCH for CCHDO, OCL for US-NODC, SPI for Scientific PI | d
Delayed Mode trajectory
10 | Thierry to update ANDRO converted D-Traj files to V3.1 as first version of D-files. | AST17 | Thierry | R | This action is pending. The conversion from 3,0 to 3,1 will start when the trajectory format checker is offically released. | ?
GDAC
11 | GDAC with AIC to keeping track on V3.1 progress by adding version information to the detailed index files | AST17 | Mike, Thierry and Mathieu | R | Not done. A status of the V3.1 progress is available in the Coriolis DAC/GDAC annual report, page 21, §"File format: transition to Argo NetCDF V3.1" http://archimer.ifremer.fr/doc/00350/46128/ | ?
12 | Provide a link from the ADMT pages to Megan's Matlab routine and to latest version of the BUFR converter | AST17 | Thierry | R | Done http://www.argodatamgt.org/Documentation/Tools | ?
13 | Audit metadata config units against allowed tech units and see if there are any outliers, then negotiate to either add units or use an approved unit. | ADMT17 | Mark, Ann | R | units are now complete and include all required for both files The FileChecker is validating CONFIG parameter units | d
14 | For Tech file : generate warning when units of technical variables don’t match the type of the field | ADMT17 | Mark | R | On hold pending completion of adding trajectory file data validation to the FileChecker | p
15 | Check data-type consistency with File name and presence or not of adjusted-parameters and reject files that don't match | ADMT17 | Mark | R | Completed. FileChecker now performs file name validation | d
16 | Implement Check for Trajectory file against reference tables ( like for profile) when the discussion on the test to be done has reached consensus | ADMT17 | Mark | R | The FileChecker validates the "header date variables" (DATE_UPDATE, etc) and the float meta-data (PLATFORM_NUMBER, DATA_CENTRE, etc). Tests for the N_MEASUREMENT and N_CYCLE variables are still under development and testing. | p
17 | Move Ref Table from Google doc to something that can be more easily be machine readable and define a workflow for the information to flow to the person that will need to review and approve changes as well as to the GDAC for the required FileChecker update. | ADMT17 | Mathieu, Mark | R | Not started | ?
18 | Modify the file checker to generate warnings for non-standard data types in the files. After 6 months, make this a rejection. | ADMT17 | Mark, Thierry | R | done | d
Format
19 | Provide clarification of data mode and parameter data mode usage : update user manual | AST17 | Thierry, Annie |  | done | d
GADR
Trajectory
20 | File format update and update the traj cookbook | AST17 | Megan |  | http://dx.doi.org/10.13155/41152 | d
21 | Profile cookbook to beupdated and posted on the official documents section of the web pages | AST17 | Megan, Thierry |  | http://dx.doi.org/10.13155/41151 | d
Question to AST
22 | Propose to AST that GDACs change QC flags to Class 3 for D-profiles that aren’t addressed when they have received feedback on issues and not corrected them (Altimetry, OA, Format check). | AST17 | Sylvie, Ann | R | Done see AST17 report will be discussed at ADMT17 | d
23 | Form a working group to address the issue of people wanting to put their floats into Argo. Their recommendation to be approved by AST | AST17 | Dean, Susan, Steve Piotrowicz, Brian, Sylvie, Breck, Annie, Megan | H | Discussion started at AST17 and will be continued at ADM17 | d
24 | ADMT requests guidance from AST as to what variables are considered of scientific value and need to be stored and which are useful for only specialist users (DM operators?) who can get that data (means, std, medians) from other sources. | AST17 | Sylvie, Ann, Brian, Susan | R | Discussion started at AST17 and will be continued at ADM17 | d
25 | Some older T/S floats remain difficult to assign to DM operators. This is reallly an AST question - do we keep that data available or make the hard decision to remove it from the GDACs? | AST17 | Sylvie, Ann | R | Done see AST17 report will be discussed at ADMT17 | d
26 | Request guidance from AST for where to store timing information - if it's a profile, put it in the C file? ? This will require a new parameter. Otherwise it can go in the B file. We recommend that sparse snapshots of time go into traj files, true profiles of time go into the core files. And if this is useful, we need to consult float manufacturers to ensure this information is provided. Pose cost/benefit question to AST and Deep Argo | AST17 | Susan and Breck to pose the questions | H | AST suggested that storing profile time be optional and put in the B files since at this time it does not seem necessary for DMQC of Core Argo. Sparse timing can go into the traj files. To be discussed at ADMT17 | d